TRI Eduthon

# TRI Something New

End-to-End Programme Proposal

Table of Contents

1. Executive Summary	3

2. Background and Objectives	3

Background	3

Objectives	3

3. Programme Timeline	4

High-Level Timeline	4

Detailed Timeline	4

4. Workshops	5

5. Competition	5

Challenge Context	5

Why This Works	6

7. Participation and Support	6

8. Judging and Awards	7

Judging	7

Award	8

9. Budget	8

10. Appendix	9

Detailed Judging Rubric	9

Judges’ Scoring Sheet	11

Committee Score Consolidation and Recognition Mapping	12

Kick-Off Email	14

Kick-Off Email #2	15

Case Study	16

# 1. Executive Summary

TRI Something New is proposed as a structured Capability-Building Eduthon that develops practical skills in Vibe Coding, Data Analytics and Power BI. The programme combines hands-on workshops with a competitive, unit-based project that will allow participants to demonstrate how effectively they can apply the capabilities learned. The revised concept retains the learning and innovation intent of the original proposal while sharpening its practical relevance. Rather than working on a shared external case, each TRI unit will apply the capabilities developed during the workshops to a real business-as-usual (BAU) challenge within their own function. They would develop a working solution and present its outcome and impact to a panel of judges.

Programme Proposition Skills are developed through workshops. Only then are they applied through a capstone project where participants will be rewarded based on their performance.

The Eduthon will run from September 2026 to January 2027. It begins with a kick-off, continues through a sequenced workshop programme, moves into capstone development and concludes with final presentations and awards.

# 2. Background and Objectives

## Background

TRI staff have access to AI tools. However, access does not automatically translate into confidence or practical capability. Conventional workshops may create awareness, but participants may have limited opportunities to integrate and apply what they have learned. The Eduthon addresses this gap by combining structured instruction, guided practice and applied competition. Participants will progressively build capabilities and then use them together to solve a realistic business problem

## Objectives

- To equip TRI staff with practical AI and digital skills that help them work smarter and more confidently.

- To make learning more engaging through hands-on practice, teamwork and healthy competition.

- To encourage participants to develop useful solutions that improve everyday work and create meaningful impact within TRI.

# 3. Programme Timeline

## High-Level Timeline

The programme is structured across four phases. Exact dates and selected PICs will be confirmed during detailed planning.

| Timeline | Activity | Key Deliverables | PIC |
| --- | --- | --- | --- |
| 25 Sept 2026 | Kick-Off | - Programme Briefing - Expectations and Judging | Ryan (Emcee) |
| October 2026 | Workshops | - Vibe Coding - Data Analytics - Power BI | Workshop Leads |
| Nov 2026 – Jan 2027 | Competition | - Unit BAU Problem Identification - Solution Development - Mentor Check-Ins | Units / Mentors |
| January 2027 | Final Presentation and Awards | - Team Presentation - Solution Demonstration - Judges Evaluation - Award Ceremony - Closing | Programme Committee / Judges |

## Detailed Timeline

Day 1: Kick-Off (25 September 2026, 3:00PM – 3:45PM)

| Time | Activity | Remarks | PIC |
| --- | --- | --- | --- |
| 3:00 – 3:05PM | Welcome and Introduction | - Welcoming Remarks - Housekeeping | Ryan |
| 3:05 – 3:25PM | Briefing on TRI Something New Eduthon | - Objectives - Timeline - Expectations - Awards - Judging | Arief |
| 3:25 – 3:30PM | Q&A & Closing | - Open floor for questions | Ryan |

Final Presentation Day (January 2027)

| Time | Activity | Remarks | PIC |
| --- | --- | --- | --- |
| 3:30 – 3:40PM | Welcome and Introduction | - Welcoming Remarks - Housekeeping | Ryan |
| 3:40 – 4:50PM | Team Presentations | - 10 Minutes / Group | Ryan |
| 4:50 – 5:00PM | Break | - Compile Judges Evaluation - Assign Award Winners | Daniel |
| 5:00 – 5:15PM | Award Presentation | - Ucop presents the award? | Ryan |
| 5:15 – 5:30PM | Closing | - Group Photo - Closing | Ryan |

# 4. Workshops

The workshop series is designed as one connected learning journey, delivered across October 2026. Each workshop builds a core capability that units will apply directly to their competition solution. The workshops (other than Vibe Coding) will be held similar to how KSS is conducted. A public case study will be used as the shared teaching example for the Data Analytics workshop, giving participants a common, realistic dataset to practise on before applying their skills to their own unit's BAU problem.

| Workshop | Purpose | Feeds Into Competition | Lead | Timing |
| --- | --- | --- | --- | --- |
| Vibe Coding | Learn to prompt effectively and use AI to support coding, exploration and troubleshooting. | Supports problem understanding, preparation, coding and exploration. | Mirza/Daniel | Oct |
| Data Analytics | Prepare the data, structure the analysis and identify meaningful patterns. | Provides a documented analysis plan and well-supported findings. | Arief | Oct |
| Power BI | Turn analysis into clear visualisations and interactive storytelling. | Enables units that choose a dashboard-based solution to build an effective, user-friendly output. | Seng | Oct |

# 5. Competition

## Challenge Context

Rather than working on a shared external case, each TRI unit will identify a genuine business-as-usual (BAU) challenge within their own function and develop a working solution using the capabilities learned across the workshop series. A solution may take any appropriate form (E.g. Python-based automation, a Power BI dashboard, a Power App) provided it demonstrably applies the capabilities developed during the Eduthon.

Central Challenge Statement How can our unit use Vibe Coding, Data Analytics and/or Power BI to solve a real BAU problem more effectively?

## Why This Works

| Design Feature | Rationale |
| --- | --- |
| Beginner-Friendly | Teams start from a problem they already understand deeply (BAU) which lowers the barrier to entry compared to an unfamiliar external case. |
| Challenging | Real BAU processes and data are often messy and organisation-specific. Teams must genuinely diagnose and solve the problem rather than apply a template. |
| Practical | Every solution addresses a real need within the unit, so the output has a genuine chance of continuing to be used after the Eduthon ends. |
| Transferable | The work mirrors TRI activities such as automating routine tasks, analysing performance, identifying trends and exceptions, and translating findings into decisions. |

# 7. Participation and Support

Participants will compete in teams and are expected to attend the core programme sessions, contribute actively to the capstone and participate in the final presentation.

| Area | High-Level Arrangement |
| --- | --- |
| Team Formation | Team will be formed within units. Each team should distribute responsibilities during the Capstone Project. |
| Participation Expectations | Participants are expected to attend the Kick-Off, Workshops, contribute to the project and present. |
| Mentoring | Mentors are there to guide teams on scope, analysis, technical blockers and presentation readiness without completing the work on behalf of participants, |
| Check-Ins | Short milestone reviews will monitor case understanding, data preparation, preliminary findings, dashboard progress and presentation readiness. |

# 8. Judging and Awards

## Judging

Teams will be evaluated using a single consolidated judging rubric covering business impact, technical execution, application of the capabilities developed during the Eduthon, and communication. These four criteria are deliberately solution-agnostic, so that a Python automation, a Power BI dashboard, a Power App, or any other solution type can be assessed fairly on the same basis. Judges will assess each criterion independently using a five-point scale:

| Score | Performance Benchmark |
| --- | --- |
| 1 | Limited: The criterion is largely unmet, unclear, inaccurate, or unsupported. |
| 2 | Developing: The criterion is partially met, but material weaknesses remain. |
| 3 | Competent: The criterion is adequately met and supported by sufficient evidence. |
| 4 | Strong: The criterion is met to a high standard, with clear evidence and only minor limitations. |
| 5 | Excellent: The criterion is met exceptionally well and demonstrates outstanding application. |

The detailed assessment criteria and performance benchmarks are provided in Appendix: Detailed Judging Rubric. Judges will record their scores using the standard form in Appendix: Judges’ Scoring Sheet. The judging rubric presented to judges will not identify or refer to the recognition categories. Judges will focus solely on evaluating the quality of each team’s work against the stated criteria. They will not be required to nominate teams for any recognition.

Following the judging process, the organising committee will consolidate the scores and apply an internal mapping between the assessment criteria and the following recognition categories:

| Recognition | Focus |
| --- | --- |
| Best Business Impact | Solution that most effectively solves a genuine BAU problem and delivers practical value. |
| Best Technical Execution | Most well-built, reliable solution, with a level of sophistication well-matched to the problem. |
| Most Creative Application | Most creative or resourceful use of the capabilities learned during the Eduthon. |
| Best Storytelling | Most compelling communication of the problem, solution and impact. |

The team with the highest consolidated score within each area will receive the corresponding recognition. The internal mapping and calculation method are provided in Appendix: Committee Score Consolidation and Recognition Mapping.

The Eduthon Champion is the programme’s principal award and will be awarded to the team with the highest overall score across the complete judging rubric. A team does not need to receive the highest score in every recognition area to become the Eduthon Champion. The award recognises the team with the strongest combined performance across the analytical, communication, dashboard and innovative application capabilities developed during the programme.

## Award

Recognition category winners (Best Business Impact, Best Technical Execution, Most Creative Application, Best Storytelling) will each receive an e-certificate and a customised Microsoft Teams profile banner.

The Eduthon Champion will additionally receive a plaque.

# 9. Budget

| Item | Quantity | Unit Price | Total Cost |
| --- | --- | --- | --- |
| Lanyard | 50 | RM 3.95 | RM 197.50 |
| PVC Card | 50 | RM 2.50 | RM 125.00 |
| Refreshments & Venue (Tea Break @ Lanai) | 50 | RM 15.00 | RM 750.00 |
| Plaque (Eduthon Champion) | 1 | RM 100.00 | RM 100.00 |
| Contingency |  |  | RM 200.00 |
| Total Cost |  |  | RM 1,372.50 |

# 10. Appendix

## Detailed Judging Rubric

Instructions to Judges

Evaluate each team using the criteria below. Scores should be based on the team’s:

- Problem understanding and solution rationale

- Build quality (e.g. the automation, dashboard, app, or other tool produced)

- Final presentation and demonstration

- Supporting documentation, where applicable

- Responses during the question-and-answer session

Each criterion must be assessed independently. A strong performance in one criterion should not automatically result in a strong score in another criterion. Judges should award a whole-number score from 1 to 5 for each criterion. The descriptions for scores 1, 3 and 5 establish the principal benchmarks:

- A score of 2 should be awarded where, performance falls between Limited and Competent.

- A score of 4 should be awarded where, performance falls between Competent and Excellent.

Consolidated Rubric

| Criterion | What’s Assessed | 1: Limited | 3: Competent | 5: Excellent |
| --- | --- | --- | --- | --- |
| Business Impact & Relevance | The extent to which the solution addresses a genuine BAU problem and the practical value it delivers (e.g. time saved, error reduction, improved decisions, cost efficiency). | The problem addressed is unclear, trivial, or not clearly BAU-related. Little or no evidence of practical value. | The solution addresses a genuine BAU problem and delivers reasonable, evidenced practical value. | The solution addresses a significant BAU problem and delivers substantial, well-evidenced value with clear potential for continued use. |
| Technical Execution & Tool Application | The quality, reliability and appropriateness of the build, including the sophistication of the tool(s) used relative to the problem being solved. | The solution is incomplete or unreliable, or the tool chosen is poorly suited to the problem. | The solution functions as intended and the tool chosen is reasonably well-suited and executed. | The solution is technically polished and reliable, with a tool choice and sophistication that is well-matched to — and elevates — the problem. |
| Application of Capabilities Learned | How effectively the team integrated the capabilities developed during the workshop series (Vibe Coding / AI-assisted tools, Data Analytics, Power BI) into their solution. | Capabilities from the workshops are barely evident or applied superficially. | Relevant capabilities from the workshops are appropriately applied to build the solution. | Capabilities from the workshops are creatively and seamlessly integrated, demonstrating clear growth in skill and confidence. |
| Communication & Presentation | The structure, clarity, persuasiveness and delivery of the team’s presentation of their problem, solution and impact. | The presentation is difficult to follow. The solution and its impact are unclear or poorly communicated. | The presentation follows a logical structure, communicates the solution and its value clearly, and is completed within the allocated time. | The presentation delivers a compelling, decision-oriented narrative. Complex ideas are communicated simply and persuasively, with confident, precise responses to questions. |

## Judges’ Scoring Sheet

Team and Jude Details

| Field | Details |
| --- | --- |
| Team Name |  |
| Judge Name |  |
| Date |  |

Score Entry

Refer to the detailed performance descriptions in Appendix: Detailed Judging Rubric before awarding scores.

| No. | Criterion | Maximum Score | Score Awarded |
| --- | --- | --- | --- |
| 1 | Business Impact & Relevance | 5 |  |
| 2 | Technical Execution & Tool Application | 5 |  |
| 3 | Application of Capabilities Learned | 5 |  |
| 4 | Communication & Presentation | 5 |  |
|  | Total Score | 20 |  |

## Committee Score Consolidation and Recognition Mapping

This appendix is intended for the organising committee and should not be included in the judging materials. The four judging criteria will be mapped internally to the four recognition categories as follows:

| Recognition | Criteria Used | Maximum Score |
| --- | --- | --- |
| Best Business Impact | 1. Business Impact & Relevance | 5 |
| Best Technical Execution | 2. Technical Execution & Tool Application | 5 |
| Most Creative Application | 3. Application of Capabilities Learned | 5 |
| Best Storytelling | 4. Communication & Presentation | 5 |
| Overall Eduthon Score | Criteria 1 to 4 | 20 |

The different maximum scores do not affect the determination of each recognition because teams are compared only against other teams within the same recognition area. The Eduthon Champion is determined using the complete score across all four criteria.

Score Consolidation

Since there is more than one judge, the organising committee will calculate the average score for each criterion. The final averages should be recorded to two decimal places.

| No. | Criterion | Judge 1 | Judge 2 | Judge 3 | Average |
| --- | --- | --- | --- | --- | --- |
| 1 | Business Impact & Relevance |  |  |  |  |
| 2 | Technical Execution & Tool Application |  |  |  |  |
| 3 | Application of Capabilities Learned |  |  |  |  |
| 4 | Communication & Presentation |  |  |  |  |
|  | Total Score | /20 | /20 | /20 | /20 |

Results Summary

| Result | Calculation | Team Score |
| --- | --- | --- |
| Best Business Impact | Criterion 1 | /5 |
| Best Technical Execution | Criterion 2 | /5 |
| Most Creative Application | Criterion 3 | /5 |
| Best Storytelling | Criterion 4 | /5 |
| Overall Eduthon Score | Criteria 1 to 4 | /20 |
| Overall Percentage |  | /100% |

Judges will not be asked to select or nominate recognition recipients. The recognition recipients will be determined as follows:

- Best Business Impact: Team with the highest average score for Criterion 1.

- Best Technical Execution: Team with the highest average score for Criterion 2.

- Most Creative Application: Team with the highest average score for Criterion 3.

- Best Storytelling: Team with the highest average score for Criterion 4.

- Eduthon Champion: Team with the highest overall average score across all four criteria

## Kick-Off Email

Subject: [INVITATION] TRI Something New!

Dear X,

You are invited to the TRI Something New Eduthon Kick-Off!

Join us as we introduce the programme’s objectives, capability-building workshops, unit-based BAU project, key milestones, participation expectations and judging framework.

- Date: Friday, 25 September 2026

- Time: 4:00 PM to 4:30PM

- Venue: x

Please respond to this calendar invitation to confirm your attendance.

You may also visit https://dt-bnm.github.io/TRI-Something-New/  to learn more about the Eduthon before the session.

We look forward to beginning this learning and innovation journey with you!

## Kick-Off Email #2

Subject: [INVITATION] TRI Something New!

Dear X,

Get ready to TRI Something New by learning new skills, exploring fresh ideas, and creating practical solutions together! 🚀

You are invited to the TRI Eduthon Kick-Off, where we will officially launch a learning and innovation journey designed to:

🤖 Equip TRI staff with practical AI and digital skills to work smarter and more confidently

🤝 Make learning more engaging through hands-on practice, teamwork, and healthy competition

💡 Encourage participants to develop useful solutions that improve everyday work and create meaningful impact within TRI

During the session, we will introduce the programme’s capability-building workshops, unit-based BAU project, key milestones, participation expectations and judging framework.

📅 Date: Friday, 25 September 2026

🕓 Time: 4:00 PM to 4:30 PM

📍 Venue: X

Please respond to this calendar invitation to confirm your attendance.

Want a sneak peek? Visit TRI Something New to learn more about the Eduthon before the session.

## Case Study

Cyclistic Bike Share

  - Background

Cyclistic is a bike-share program operating a fleet of geotracked bicycles across a network of docking stations. Riders access bikes under two pricing structures: single-ride or full-day passes (“casual riders”) and annual memberships (“members”). Cyclistic's stated finding is that annual members are the more profitable segment, which sets up the case study's business task.

  - Business Task

  - Design a marketing strategy aimed at converting casual riders into annual members.

  - Identify how annual members and casual riders use Cyclistic bikes differently.

  - Why would casual riders buy a membership?

  - Data Structure

Each ride record typically includes the following fields:

- ride_id — unique identifier per ride

- rideable_type — classic, docked, or electric bike

- started_at / ended_at — ride start and end timestamps

- start_station_name / start_station_id and end_station_name / end_station_id

- start_lat / start_lng and end_lat / end_lng — station coordinates

- member_casual — rider type (member vs. casual)

  - Potential Workflow

Ask — confirm the business task and stakeholders (marketing director, analytics team, executives). Prepare — consolidate 12 months of monthly CSVs; check licensing and data currency. Process — clean timestamps, handle missing station data, derive ride length and day-of-week fields. Analyse — compare ride duration, frequency, time-of-day/day-of-week patterns, etc. Share — visualise differences (e.g. weekday vs. weekend usage) for a non-technical audience. Act — translate the differences into a targeted conversion campaign.

HR Dataset

  - Background

This notebook is an exploratory data analysis (EDA) exercise on an employee-level HR dataset. The stated purpose of this class of dataset is to help an HR function understand which employee characteristics are associated with attrition, so that retention interventions can be targeted rather than generic.

  - Business Task

  - Understand which employee attributes are most associated with attrition.

  - Surface patterns across demographic, role, compensation, and satisfaction variables.

  - Produce visual, non-technical summaries that an HR audience can act on.

  - Data Structure

Datasets of this type typically consist of one row per employee, with fields spanning several categories:

- Demographic — age, gender, marital status, distance from home

- Employment — department, job role, job level, years at company, overtime status

- Compensation — monthly income, salary hike percentage, stock option level

- Satisfaction / engagement — job satisfaction, environment satisfaction, work-life balance

- Outcome variable — attrition (yes/no)

  - Potential Workflow

Data quality check — inspect shape, data types, missing values, and duplicates. Univariate analysis — distribution of individual variables (e.g., age, income, tenure). Bivariate analysis — relationship between each variable and the attrition outcome, usually via grouped bar charts, box plots, or crosstabs. Correlation analysis — a correlation matrix or heatmap across numeric fields to flag multicollinearity or strong associations. Segment framing — grouping employees by department, role, or tenure band to compare attrition rates across segments.